## PO-INV
Sr. No. | Project Name | Module | Knowledge Area | Knowledge Objects | Description | Status | Planned Start Date | Planned End Date | Planned Hours | SME Name | KT Receiver | Conference Call Number | Meeting Room No - France | Meeting Room No - India | Remarks
1 | Michelin ERP-BB | SPI Activity | Overview | Michelin ERP-BB Onboarding | Onboarding Kit PPTs | Completed | 2017-12-11 | 2017-12-11 | 1 | Abhishek Dharme | Naveen, Pavani
2 | Michelin ERP-BB | SPI Activity | Overview | Introduction | EBS R12 basics Basic Concepts on Oracle R12 EBS and application knowledge | Completed | 2017-12-12 | 2017-12-12 | 1 | Abhishek Dharme | Naveen, Pavani
3 | Michelin ERP-BB | SPI Activity | Michelin Specific | Packaging & Deploying activities | ACMP Customization Manager, Understanding of how to make custom packages used for deployment with demo | Completed | 2017-12-12 | 2017-12-12 | 1 | Abhishek Dharme | Naveen, Pavani
4 | Michelin ERP-BB | SPI Activity | Michelin Specific | Packaging & Deploying activities | ACMP Patch Manager Deploying patches, understanding process | Completed | 2017-12-13 | 2017-12-13 | 1 | Abhishek Dharme | Naveen, Pavani
5 | Michelin ERP-BB | SPI Activity | Michelin Specific | Other tools & applications | Subversion performing checkout and checkin, navigation through files and directories in SVN JIRA Checking of FOP's and navigation in JIRA COMA TRA Navigation through COMATRA and Updating activities of ACMP File Zilla About file zilla and copying files to unix environment SQL Developer Performing verification steps after migration | Completed | 2017-12-14 | 2017-12-14 | 1 | Abhishek Dharme | Naveen, Pavani
6 | Michelin ERP-BB | SPI Activity | Michelin Specific | ACMP troubleshooting | Troubleshooting errors, checking log | Completed | 2017-12-15 | 2017-12-15 | 1 | Abhishek Dharme | Naveen, Pavani
7 | Michelin ERP-BB | SPI Activity | Michelin Specific | CM process | CM Plan, process flow | Completed | 2017-12-18 | 2017-12-18 | 1 | Abhishek Dharme | Naveen, Pavani
8 | Michelin ERP-BB | SPI Activity | Michelin Specific | Manual migration (through Unix) | Unix Deployment using adpatch, manual migration, checking driver files and Log | To Start | 2017-12-19 | 2017-12-19 | 1 | Abhishek Dharme | Naveen, Pavani
9 | Michelin ERP-BB | SPI Activity | Michelin Specific | Access request for Configuration Factory | Raising access request | To Start | 2017-12-19 | 2017-12-19 | 1 | Abhishek Dharme | Naveen, Pavani
10 | Michelin ERP-BB | SPI Activity | Michelin Specific | CM point of contact | SPI and DBA information | To Start | 2017-12-20 | 2017-12-20 | 1 | Abhishek Dharme | Naveen, Pavani
11 | Michelin ERP-BB | SPI Activity | Michelin Specific | Time Card/Clarity/Timecharts | Time card/Monthly Clarity | To Start | 2017-12-21 | 2017-12-21 | 1 | Abhishek Dharme | Naveen, Pavani
12 | Michelin ERP-BB | SPI Activity | Michelin Specific | Shadowing SPI activities | Shadowing SPI activities | To Start | 2017-12-21 | 2017-12-21 | 1 | Abhishek Dharme | Naveen, Pavani
13 | Michelin ERP-BB | SPI Activity | Michelin Specific | Reverse Shadowing SPI activities | Reverse Shadowing SPI activities | To Start | 2017-12-22 | 2017-12-22 | 3 | Abhishek Dharme | Naveen, Pavani
1 | Michelin ERP-BB | AOL Activity | Michelin Specific | Access requirement | User Create/update, Responsibility assignment | Completed | 2017-12-12 | 2017-12-12 | 2 | Abhishek Dharme | Naveen, Pavani
2 | Michelin ERP-BB | AOL Activity | Michelin Specific | AOL setups | Role Create/Update | To Start | 2017-12-13 | 2017-12-13 | 1 | Abhishek Dharme | Naveen, Pavani
3 | Michelin ERP-BB | AOL Activity | Michelin Specific | AOL setups | Request Group Create/Update | To Start | 2017-12-14 | 2017-12-14 | 1 | Abhishek Dharme | Naveen, Pavani
4 | Michelin ERP-BB | AOL Activity | Michelin Specific | MO setups | Create / Update security profile Assign profiles at different level | Completed | 2017-12-15 | 2017-12-15 | 1 | Abhishek Dharme | Naveen, Pavani
5 | Michelin ERP-BB | AOL Activity | Michelin Specific | MO setups | Program addition/removal to Responsibility | Completed | 2017-12-18 | 2017-12-18 | 1 | Abhishek Dharme | Naveen, Pavani
6 | Michelin ERP-BB | AOL Activity | Michelin Specific | Troubleshooting | Depends on the context of FOP | To Start | 2017-12-19 | 2017-12-19 | 2 | Abhishek Dharme | Naveen, Pavani